Short Program Review of Child Health Program

20-23 September 2010

College of Natural Resources, Lobesa

Acknowledgement

This “Short Program Review of Child Health” is the outcome of a rich but demanding process of consultation, gathering data and information, writing, editing and compilation.

The process has involved many program staff, either directly through written contribution and consultation or indirectly through the comments provided. Reaching this stage is indeed a major achievement and Ministry of Health would like to convey its sincere acknowledgement to the all individuals for their valuable contributions towards successful completion of the Short Program Review on Child Health 2010.

List of Participants

- Dr. K.P Tshering, Pediatrician, Thimphu

- Dr. HP Chettri

- Dr. Dhruptho Sonam, CMO, Paro

- Dr. TB Rai, Medical Specialist

- Dr. Shukhrat Rakhimdjanov,Health Specialist,UNICEF

- Dr. Chandralal Mongar,UNICEF

- Mr. Tandin Dorji, CPO, Thimphu

- Mr. Rinchen Namgyal, Sr. PO, DHSP, DMS

- Ms. Deki Pem, Lecturer, RIHS, Thimphu

- Mr. Tshewang Dorji Tamang, Programme Officer, Thimphu

- Ms. Ugyen Zangmo, Sr PO, Nutrition, DoPH

- Mr. Dopo, Information Officer, BHMIS, MoH

- Mr. Dorji Gyeltshen, ADHO, Dagana

- Mr. Moelam Dorji, HA, Norbuling BHU, Sarpang

- Ms. Dema, HA, Tala, Chukha

- Mr. Sonam Wangdi, APO, RH

- Mr. Sonam Zangpo, Programme Officer, Thimphu

- Ms. Yeshey Chhoden,UNICEF

Table of Contents

1.	Background	5

2.	Methodology	5

3.	Situation Analysis	6

3.1.	Child Mortality: Characteristics-Scale and Distribution	6

3.2	Underlying determinants and existing bottlenecks at level of Health System service delivery	7

3.3	Underlying determinants and existing bottlenecks at level of community/household.	8

4.	Short Programme Review Problems and Specific Recommendations	10

4.1	Problems and recommendations at Policy, Planning and Management level.	10

4.2	Problems and recommendations in the area of human resources.	11

4.3	Problems and recommendations in communication/IEC activity area.	11

4.4	Problems and recommendations in area of development of community support.	12

4.5 	Problems and recommendations in area of development of community support.	12

4.6	Problems and recommendations in area of monitoring and evaluation.	12

5.	Summary Recommendations	13

Annexes Worksheets (1-7)	14

- Background

The MDG 4 calls to reduce under-five child mortality by two-thirds between 1990 and 2015. Better management of existing health systems and resources is one essential element required to apply interventions more effectively in order to reach the MDGs.

RGoB set the goals to meet MDG 4 and 5 as following:

- Reduce IMR to 20 per thousand live births by 2013

- Reduce under five mortality to 30 per thousand live births by 2013

- Reduce MMR to less than 140 per 100,000 live births by 2013

Following objectives were formulated to meet the achievement of MDGs

- Reduce micronutrient deficiencies

- Sustain immunization coverage above 95%

- Promotion of infant and young child feeding practices

- Expand comprehensive EmONC services from 7 to 15 by 2013

- Improve access to safe sanitation to near 100%

- Sustain access to safe drinking water to near 100%

To assess progress toward program goals and objectives meeting MDGs and to assess how well the program implemented its plans in to deliver child health interventions, the MoH in collaboration with UNICEF conducted Short Programme Review of Child Health Programme.

The objectives of Programme Review were to:

- Identify the problems the Child Health program has faced and suggest solutions;

- Develop recommendations about what the program needs to do;

- Decide on next steps for incorporating recommendations into the workplan.

- Methodology

The review team comprising of officials from different programmes of MoH, technical experts and officials from UNICEF conducted Short Programme Review (SPR) on the status of maternal, newborn and child health using the various available documents over a period of 4 days. The review focused on Child health programmes such as Maternal Health, Immunization, Nutrition, Infant and Young Child feeding practices, VHW, Malaria, IMNCI, for all children from birth to 59 months, including neonates and infants. The team reviewed how well the child health interventions were implemented.

Based on the review findings, participants identified the main problems for further analysis. The team discussed and identified feasible solutions. Then they used the identified solutions as the basis and developed recommendations about what the program should do in major activity areas.

The following seven steps review process was followed for the review of SPR:

Step 1:	Using worksheet 1 and 2 the participants reviewed the goals and objectives of the program and the status of maternal and child health.

Step 2:	The team used worksheets 3 and 4 to analyze the current child health intervention packages and the way it is being delivered. Interventions that are not yet included in the programmes were identified and recommended for incorporation in future. The team also reviewed coverage indicators for child health.

Step 3:	The team assessed using worksheet 5 whether the program implemented activities in each activity area fully, partly, or not at all, and identified strengths and weaknesses for each activity area.

Step 4:	Using worksheet 6, the participants summarized the main problems that have limited the ability to deliver interventions that have been identified as having low coverage.

Step 5:	The solutions for each of the problems were identified and recommendations suggested for intervention. The team reviewed and discussed how well the program implemented activities using Worksheet 7.

- Situation Analysis

## 3.1.	Child Mortality: Characteristics-Scale and Distribution

In 2008, Bhutan’s infant mortality rate (IMR) was 54 per 1000 live birth and under-five mortality (U5MR) rate about 81 per 1000 live birth, which is a considerable drop from the 1990 baseline of 91 IMR and 148 U5MR. The trend shows an annual reduction of U5MR was 3.3%, which is lower than the required 4.2% annual reduction to meet MDG 4.

Information on neonatal mortality is scarce in the government health statistics. However, existing statistics show that the neonatal mortality rate has decreased from 38 per 1000 live births in 2000 to 30 in 2004. Majority of infants or 54% die within a month of their birth.

Analysis of 2005 Census datarevealed that the highest U5MR was recorded at Chukha (89 per 1000 live births), Trashigang (88.6) and Samdrup Jongkhar (87) districts which are the same districts with  highest IMR. In 2003, the estimated IMR of 73 and U5MR of 115 per 1000 live births in rural Bhutan were 40% and 49% respectively above the urban areas (IMR-52/1000 and U5MR-77/1000 live births). IMR and U5MR are equally high in eastern regions such as Samdrup Jongkhar, Lhuntse, Monggar and Trashigang districts.

Though under-nutrition status, particularly national average for stunting is 37%. However, stunting prevalence for children below 60 months was the highest in the eastern region at 44%, and almost equally 33% and 34% in the western and central regions. In accordance with WHO classification, stunting rate in Eastern region exceeds 40% thus classified as critical. Most of the districts with IMR and U5MR above the national level of 40.1 and 60.6 were also from southern and eastern regions. This clearly shows that the under-nutrition due to poverty is contributing to the child mortality.

Children start to become malnourished even in the womb. In 1998 about 24% of children born in health centers had low birth weight (less than 2.5 kg) though the proportion has fallen to 9.3% in 2008. 10.2% of birth in 2005 occurred in teenage (15-19 years) mothers. Teenage pregnancy leads to low birth weight babies who are highly vulnerable to neonatal deaths. Again some southern and eastern districts have as high as 13% teenage pregnancy.

## 3.2	Underlying determinants and existing bottlenecks at level of Health System service delivery

Most children born with normal weight also become malnourished in their first and second years. Stunting among children is attributed to poor complementary feeding practices and low rate of exclusive breastfeeding, which remains 10.4% for babies under 6 months. The stunting rate increases from 6 month onward. The same pattern attributed to underweight.

Coverage of care. Though the primary health care coverage has reached 95% of the population, the government is striving to reach the remaining 5% who are most in need of such services. An effective referral system at the outpatient health care level is necessary to reach these un-reached populations. Antenatal coverage has increased from 57% ANC (1 visit) in 2000 to 94% (ANC 2-4) in 2009 and coverage of Tetanus Neo-natorum is sustained at 86%. During antenatal coverage all women are provided with calcium supplementation, Iron Folic acid tablets and Vitamin C .Vitamin A postpartum rate is above 88% and community are aware of the importance of Vitamin A supplementation. However, full antenatal coverage (4+) remains low (44%). Institutional delivery increased from 27% in 2002 to 62% in 2009 and vaccination coverage for all antigens sustained at 95% and above.

A major drawback for trained health staff to retain their skills is the low patient load, especially in health facilities located in remote and rural areas. The World Health Organization (WHO) standard is 175 births per skilled birth attendant per year to ensure that they retain their competency in midwifery skills. In a sparsely populated country like Bhutan, this may be difficult, as there are only 3-5 deliveries per year in some of the remote BHUs. This affects quality of maternal health care services. In addition, high rate of neonatal death due to infections is also questioning hygiene aspects during the deliveries either at home or health facilities.

Quality of care. Some gaps need to be addressed through more integration and quality of services. When 94% of pregnant women do attend ANC2-4, an important dropout rate (only 44% ANC4+) and a skilled attendant at birth only at 62%, demonstrate that quality of care during antenatal care, pertinent and adequate counseling is not sufficiently provided. Lack of data on coverage on postnatal care makes difficult to analyze quality of services after delivery. Home visits by BHU health workers practiced in exceptional cases, such as for medical checkup after home delivery. Mothers after delivery are advised to come for postnatal visit, but very few come within first week after delivery and majority comes after one month for vaccination or in case newborn is sick.

The quality of continuum of care, particularly antenatal care remains poor. Low PNC visit and poor knowledge on newborn danger signs is significantly correlated. Key life-saving interventions like temperature management, clean cord care and initiation of breast feeding should also be re-visited. This quality of care during ANC and skilled delivery is again questioned by the very high post natal for Vit A rate, showing how all women are eager to have a first consultation for their newborn. When a mother needs advise on lactation, trained specialist does not exist at district level let alone at BHU. Children’s health cards show that though immunization coverage is high, quality in regard to timeliness and according to schedule is an issue. Gender sensitive staffing and adequate health workers in remote health units pose a challenge. Limited number of female health workers might discourage expectant mothers to deliver their babies at the health care centre.

Availability of interventions. The 16 key evidence interventions at different periods based on Lancet/BMJ/Cochran Series are mostly included in the midwifery standard and essential new born care protocol except preconception, intermittent presumptive treatment for malaria, detection and treatment of asymptomatic bacteriuria and community based pneumonia case management. However the coverage of these interventions are mainly available in all the hospitals and BHU I except corticosteroid for pre-term labour and detection and management of breech caesarean section which are available only in the hospitals with gynecologists.

## 3.3	Underlying determinants and existing bottlenecks at level of community/household.

Care seeking behaviour during pregnancies. As mentioned above there is poor knowledge of mothers about pregnancy and delivery. Furthermore, most expectant mothers walk or need to be carried for hours to reach a health centre for EmOC. Most family members delay the decision to seek medical care because the knowledge on danger signs during pregnancy and delivery is poor and because they consider it safe to deliver in the privacy of one’s own home.

Household and community care practices. Family behaviours and practices on newborn care like cord care, early initiation of breastfeeding, delayed bathing, kangaroo mother care especially for low birth weight infants are still lacking. A large proportion of respondents (69%) agreed that a baby should be given a bath right after birth. 35% of the population think that giving water during diarrhea will worsen the child health. This may be attributed to the fact that information on home-based newborn care is not adequately conveyed to mothers or families during ANC and PNC visits and immunization session for young children in the outreach clinics. In addition, VHWs are not yet trained on newborn care.

However, there is still a lack of data on household and community care practices, including management of diarrhea and pneumonia. Further KAP-research is required as these are important killers of children under five. Community based management of pneumonia is not practiced in Bhutan. Only health workers at the health facilities provide antibiotics to the people with pneumonia, as the MoH is concerned that the community or Village Health Workers will not use the antibiotics properly, leading to antibiotic resistance.

Feeding practices. Stunting among children is attributed to low rate of exclusive breastfeeding and poor complementary feeding practices. 82% of women initiate early breastfeeding, but only 10% breastfeed exclusively for the first six months as introduction of complementary feeding traditionally starts early. Thus, awareness and knowledge on the importance of exclusive breastfeeding and appropriate complementary feeding practices is still low among families. According to the 2010 KAP study 43% of mothers reported that breast milk alone is not sufficient for the baby during the first six months of age. 29% of mothers agreed that artificial feeding does not harm the baby’s health and 29% also agreed that a piece of butter must be fed to a baby right after birth. High levels of protein-energy malnutrition may be explained by mothers’ inability to or unawareness of the need to feed their children with protein-rich food like eggs or meat.

Care-seeking knowledge, attitudes and practices. The 2007 Bhutan living Standard Survey showed that approximately 22% of the people who became sick do not seek either government or private health services. 26% of those who did not seek any health services did so because of lack of transportation. Traditionally Bhutanese especially in rural areas mostly rely on the consultation with traditional healer or religious practitioners. This might delay the decision to seek medical services. According to 2000 National Health Survey, 18% of people sought advice from a traditional lama. After performing the rituals, two-thirds of these subsequently consulted with modern health services. This means only 6% sought the services from traditional practitioners, similar to the findings of the 2007 Bhutan Living Standards Survey. Low utilization of services is also due to unattractive and unfriendly health facilities for expectant mothers. Low literacy rate among women (43%) and even lower in rural areas (39%) might also contribute to low utilization of health services.

Household poverty. 23% of the population falls under the poverty line, with significantly higher levels in the East and the South, especially in remote rural areas. There is a direct association between IMR/U5MR and socio-economic variables such as (i) possession of TV meaning economically better off, (ii) mothers literacy, (iii) access to electricity and (iv) closeness to road heads. Areas with high IMR/U5MR are also areas with higher than average poverty levels.

- Short Programme Review Problems and Specific Recommendations

Six major activity areas have been analyzed, problems revealed, causes of the problems identified, for each problem solutions developed and for each activity area the recommendations are proposed.

- Policy, planning and management

- Human resources and training

- Communication/IEC

- Development of community supports

- Strengthening health systems

- Monitoring and evaluation

The review team worked on seven worksheets on different activity area and identified problems for which recommendations were suggested for most of the problems.

## 4.1	Problems and recommendations at Policy, Planning and Management level.

In-depth analysis by the review team revealed the following problems at policy, planning and management level which affected implementation of the child health programmes:

- No specific programme unit looking after Child Health Programme whereas for Maternal health there is one (RH programme unit)

- Lack of knowledge and skills in the program planning and management

- Unfunded activities reflected in the AWP/ Ad hoc activities

- No proper data on births and deaths

- Inadequate/quality of data on ANC/PNC/neonatal deaths/immunization coverage

To address these problems, following specific recommendations are proposed:

- To form Child Health Advisory Committee(CHAC) at the MoH to guide and provide technical assistance to all child health related programs

- All existing program officers including DHOs to be mandatorily trained on program planning and management.

- To reduce the neonatal and maternal mortality postnatal home visit should be made mandatory.

- PNC guidelines and home visit check list to be developed for BHU health workers.

- In collaboration with MoHCA and NCWC, develop a mechanism for vital registration and support its implementation through training, supervision, monitoring and evaluation.

- Early childhood care and development (ECCD) is an important component of IMNCI and had to be incorporated in the IMNCI module.

- To complete the linkage between the BHUs and hospitals on IMNCI referral the WHO module on hospital based IMNCI should be adopted and the capacity of health workers should be built.

- The child health program (RH, Nutrition, EPI, IMNCI, ARI/CDD) review should be conducted twice in five year plan.

  - Problems and recommendations in the area of human resources.

Across all the child health related programmes the problems in the area of human resources/training activity has been formulated as following:

- Dependence on other countries for most HR development and resources

- In service training planned on annual basis only

- Release of field staff and facilitators for in-service trainings

- In appropriate deployment of skilled human resources

- Inadequate hands on training

- Quality of services provided by the health workers

Implementation of below specific recommendations proposed by the review team will improve effectiveness and efficiency of the training programmes:

- Conduct assessment of the quality of services provided by the health workers

- HRD to improve the coordination of in service trainings

- HRD to deploy health workers based on their skills

- One month pre-service orientation program for all new health workers on program aspects (RIHS, medical officers and other graduates)

  - Problems and recommendations in communication/IEC activity area.

The review team using survey data as well as process indicators was able to identify across all programmes the following problems on communication/IEC activity area:

- Low knowledge of mothers on danger signs during pregnancy, delivery and post-natal period.

- Prevailing misconception on childhood illnesses and care

- Low quality of health communication and education activities

- Poor ANC +4 visits (44%) affected due to low quality services

- Almost no PNC coverage

- Extremely low exclusive breastfeeding rate (10%) significantly correlated with early introduction of complementary feeding.

The review team strongly suggests that following specific recommendations will help to improve communication component of maternal and child health programme in short period of time:

- Form a working group to develop a communication strategy and action plan for child health.

- Ensure that communication strategy and action plan for maternal and child health address sufficiently in annual work plans, implemented and monitored by the working group.

- Ensure budget for communication action plan.

- Promotion of maternal nutrition program to reduce low birth weight

  - Problems and recommendations in area of development of community support.

The results of surveys, available data and feedback from field level staff such as BHU health workers and ADHOs showed that the area of development of community support has two major problems:

- Insufficient utilization of community support.

- High dropout rate of VHWs

The review team strongly proposed that the following specific recommendations are of paramount importance to boost the community based interventions:

- Review effectiveness of the VHW program

- Health workers should carry out supportive supervision of the VHWs

- Sustain the incentives that are currently in place and find other forms of motivation/incentives

- Sustain annual regular training for VHWs

- Organize meeting with the best two VHWs from each Dzongkhag once in two years

- Development and implementation of community health package

## 4.5 	Problems and recommendations in area of development of community support.

The review team expresses the concern that the following problems at the health system level will pose danger of interruption of quality and continuity of maternal and child health services:

- Inadequate human resource at the BHU level

- Inadequate coverage of in-service training for certain categories of health workers

- Shortage of some essential drugs

The team felt that addressing three specific recommendations at this stage would suffice to improve and strengthen health system area:

- Reinforce the existing RCSC rule of rural placement by HR/Dzongkhags

- Conduct audit of under five deaths to find causes of child deaths and identify area to focus

- With immediate effect DVED to follow up with procurement of essential drugs

## 4.6	Problems and recommendations in area of monitoring and evaluation.

The review team unanimously agreed that the problems identified in the area of monitoring and evaluation are common to all  programmes and has not been addressed in the past adequately:

- No follow up after in service trainings

- Lack of regular  monitoring and supervision

Below recommendations should be implemented immediately across all programmes to improve the impact of the interventions:

- To implement continuum of care monitoring at BHU and district level\

- Institute a follow up plan after every training.

- ToT and cascade training including monitoring and after-training supervision to be budgeted together.

- Conduct impact assessment on the trainings/interventions.

- Summary Recommendations

Analysis of the health status indicators and trends, main functions of the health system, as well as of essential activities in Bhutan was performed. It revealed problems and challenges the country faces in providing essential MCH care, in terms of target population’s access to it, coverage of interventions, and quality of provided services. The report highlighted that trends and challenges on Child Health needs to be accelerated to meet MDG4 and the Child Health should be placed at the forefront of the MoH policy. The report selected the critical recommendations for the health system and emphasizes implementation of below recommendations as urgent and highest priority:

- To form Child Health Advisory Committee(CHAC) at the MoH to guide and provide technical assistance to all child health related programs

- Initiate and make a mandatory at least one postnatal home visit after delivery at BHU level.

- Early childhood care and development (ECCD) is an important component of IMNCI and had to be incorporated in the IMNCI module.

- Build the capacity of all hospitals on Basic Pediatric Care (Hospital IMNCI)

- Establish one month pre-service orientation program for all new health workers on program aspects (RIHS, medical officers and other graduates)

- Develop a communication strategy and action plan for child health and form a working group to monitor its implementation.

- Conduct audit to find causes of under five deaths and identify areas to focus

- Implement simple Continuum of Care monitoring form at all BHUs and district level CHUs

# Annexes Worksheets (1-7)

Using Data

for Reviewing Child health Program

(Short Program Review)

Worksheets by Step

Step 1		Where are we going?

Worksheet 1: Goals and objectives of the child health program

Worksheet 2: Status of maternal, newborn and child health

Step 2		Are  interventions reaching women and children?

Worksheet 3: Child health interventions and how they are delivered;

Worksheet 4: Coverage indicators for child health.

Step 3	How well are program activities being implemented?;

Worksheet 5: Review how well the program implemented activities.  Assess whether the program implemented  activities in each activity area fully, partly or not at all; Determine why the program failed to implement activities or implemented them in an unsatisfactory way; summarize program strengths and weaknesses.

Step 4		What are the main problems the program has faced?

Worksheet 6: Identify the main problems.  Problems have limited the ability to deliver interventions.

Step 5		What are solutions and recommendations for problems?

Worksheet 7:  Describe solutions and recommendations – for each main problem area.  These should be feasible and realistic.  They will be incorporated into the next workplan.

Step 1

Where are we Going?

Worksheet 1: Goals and objectives of the child health program

Worksheet 2: Status of maternal and child health

1.1.	Review the goals and objectives of the child health program

Goals and objectives provide the overall direction for the child health program.

Goals

Goals are long-term improvements in child health and survival expected by a program.

Goals are measured as changes in childhood nutritional status, morbidity or mortality (health impact).   Goals set the direction for all program activities.  Since they require changes in morbidity or mortality, goals may take 5 – 10 years or longer to achieve.

Example goals

- Reduce under-5 child mortality to 65/1000 live births by 2015

- Reduce infant mortality to 50/1000 live births by 2015

- Decrease the prevalence of stunting (<-2SD height for age ) in children under 5 to 	25% by 2015

Objectives

Objectives are the medium-term changes in intervention coverage that are expected by a program.

Objectives are expected to change as the program is implemented - in the short or medium term (1-2 yearly).   If objectives are not met, then it is unlikely that long term reductions in child morbidity and mortality will occur – and program goals will not be met.

Example objectives

General

- Improve coverage of interventions to prevent and manage pneumonia, diarrhea, 	malaria, newborn problems and under–nutrition, by improving the quality of 	community and facility-based services and health education

- Strengthen health system capacity for sustained management and delivery of high 	quality health services

Specific

- Increase the proportion of infants under 6 months who are exclusively breastfed

- Increase the proportion of pregnant women who received 2 or more TT immunizations during their pregnancy

- Increase the proportion of children with diarrhea in the previous 2 weeks who received ORT

Read Worksheet 1: Goals and objectives of the child health program

These will be reviewed and discussed in plenary session.

Worksheet 1: goals and objectives of the child health program

| Program Goal | Program Objectives |
| --- | --- |
| - Reduce child mortality and morbidity - Reduce maternal mortality | - Reduce IMR to 20 per thousand live births - Reduce under five mortality to 30 per thousand live births - Reduce MMR to less than 140 per 100,000 live births - Reduce micronutrient deficiencies - Sustain immunization coverage above 95% - Promotion of infant and young child feeding practices - Improve access to safe sanitation to near 100% - Sustain access to safe drinking water to near 100% - Expand comprehensive EmONC services from 7 to 15 by 2013 |

1.2.	Review the status of maternal, newborn and child health

Review and discuss morbidity and mortality data in worksheet 2: indicators for maternal, newborn and child health status.

These will be reviewed and discussed in the large group.

For each measurement, ask the following questions:

- Are data available?

- Has the target been met? (if a target has previously been established)

- How has it changed over time?  Is it going up or going down?

- Does it differ between different regions or groups?

- Are there any problems with the validity or reliability of the data – are new or different methods needed?

Summarize findings on Worksheet 2:

Tick indicators with positive results

Trends are downwards

Targets have been met

Cross indicators with negative results

Trends are upwards or static

Targets have not been met

Differences between sub-groups

Shade indicators where data are needed

Describe how data will be collected in the future

Worksheet 2: Indicators of maternal, newborn and child health status

| Data Required | Measures | Baseline data (year and source) | Most recent data (year and source) | Target | Differences by region or group (highest/lowest) |
| --- | --- | --- | --- | --- | --- |
| Neonatal deaths | Neonatal death rate | 52/12,538 *1000=4.1 (Note: Numerator from ABH 2010, denominator from PHCB 200% (2005) | 144/13362**1000= 10.8 (MNDI report 2010) Note: Total no. of delivery was used as proxy LB | <10 | H= Chukha |
|  | Neonatal mortality as a proportion of IMR and U5MR | 52/503*100=10% 52/772=6% 2005/(AHB 2010) |  | NA |  |
|  | Causes of death | Prematurity- 35% Birth asphyxia=22% Antepartum=7% Congenital=4% Unknown=4% Others=28% (MNDI Report 2010) |  | Reduce prematurity and birth asphyxia |  |
| Maternal deaths | Maternal mortality ratio | 255/100000 (NHS 2000) | 15/13362*100000=112 | 140 by 2015 ( MDG) |  |
|  | Causes of death | PPH- 55% Septicemia- 14% Obstructed labour-7% Others-24% (April, 2005-June 2006 MDR 2007) | PPH- 30% Medical- 23% PIH- 8% Ruptured uterus-8% Unknown-15% (MNDI 2010) |  |  |
| Low birth weight | Prevalence of low birth weight | 8.5% (Hospital based study 2005) | 9.3% (Hospital and BHU based study 2006-07) | <5% | H=western region L= central region |
| Infant mortality rate | Infant mortality rate | 40.1 (PHCB 2005) | Await BMICS 2010 result | 20 by 2013, 10 FYP) |  |
|  | Infant mortality as a proportion of all child mortality | 65% (PHCB 2005) | Await BMICS 2010 result |  |  |
|  | Causes of death | NA | NA | NA | NA |

Worksheet 2: Indicators of Maternal, newborn and  child health status

| Data Required | Measures | Baseline data (year and source) | Most recent data (year and source) | Target | Differences by region or group (highest/lowest) |
| --- | --- | --- | --- | --- | --- |
| Child deaths | Under 5 mortality rate | 61.6/1000 | Awaits BMICS 2010 | 30 (10fy plan) |  |
|  | Causes of death | NA | NA | NA | NA |
| Child morbidity | Prevalence of childhood illnesses: pneumonia, diarrhea, malaria (fever), measles | P=20% D=21% Malaria: 1/10,000 (2009 program report) | 4.3% (2007) 11% (2006) | 15% (10fy plan) 10% (10fy plan) |  |
|  | Proportion of children who are positive among the total HIV positive | 9.5% (program report 2007) | 8.2% (program report 2010) | NA HIV to look into the target |  |
| Under nutrition | Prevalence of low weight for height (z-score -2 or less) | 2.6% Anthropometric survey 1999 | 4.6% National Nut and IYCF study 2008 | Sustain at <5% | H=western regional L= central region |
|  | Prevalence of low height for age (z-score -2 or less) | 40% Anthropometric survey 1999 | 37% National Nut and IYCF study 2008 | 30% (10FYP) | H= eastern region L= central |
|  | Prevalence of low weight for age (z-score -2 or less) | 18.7% Anthropometric survey 1999 | 11.1% National Nut and IYCF study 2008 | 15% (MDG) | H= western region L= eastern region |
| Micronutrient deficiencies | Prevalence of anemia among children age between 6-36 months (Hb ,11g/dl) | 81% National anemia survey 2002 |  | 60% (10fy plan) | For this particular study the Hb cut off level used is 11g/dl |

Summary of Worksheet 2 – health impact indicators

Health status indicators - program is doing enough now

IMR: 40 per thousand live births

U-5 MR: 62 per thousand live births

Childhood Immunization coverage:98% (Immunization coverage survey 2008)

Low birth weight: 9.3% (National Nutrition and IYCF study 2008)

Vitamin A Deficiency: 2.6% (Vitamin A Deficiency survey 2000)

Malaria incidence in population at risk: 1/1000 (AHB 2010)

Health status indicators - program needs to do more

U-5 MR: 62 per thousand live births

MMR: 255 per 100000

Stunting for under five: 37%(National Nutrition and IYCF study 2008)

Exclusive breastfeeding for the first 6 months: 10%(National Nutrition and IYCF study 2008)

Introduction of appropriate complementary food at 6 months: 20.8% (National Nutrition and IYCF study 2008)

Iron Deficiency anaemia for 6-36 months: 81% (National Anaemia survey 2002)

ORT corners in health centres: 31% (program report 2009)

Access to safe drinking water: 83%. (AHB 2010)

Access to safe excreta disposal:91% (AHB 2010)

Under five pneumonia incidence: 103.1/1000 (AHB 2010)

Under five diarrhoeal incidence: 289.2/1000 (AHB 2010)

Step 2

Are Interventions Reaching Women and Children?

Worksheet 3: Child health interventions and how they are delivered

Worksheet 4: Coverage indicators for child health

1.3.	Describe current child health interventions and how they are delivered

Review and discuss Worksheet 3 – Child health interventions and how they are delivered

Each small group reviews a different level of the continuum of care (pregnancy, delivery and immediate post-delivery, neonatal period, infants and children 1-59 months).

Review and discuss

- Interventions that are currently delivered

- Levels at which interventions are currently delivered

- Whether health workers are trained to give 2 or more interventions at the same time (intervention packaging).  Describe current packages/training courses

- Whether interventions are available in all geographic areas or whether their availability is limited

Summarize findings on Worksheet 3

Tick interventions that are currently included in the program

Shade interventions that are not currently implemented at all levels of the health system – and that need to be delivered at other levels

Star interventions that have a limited geographic reach

WORKSHEET 3: Child health interventions and how they are delivered

PREGNANCY

| Interventions | Included in program? Tick if yes | Level at which intervention is delivered Tick levels |  |  | Implemented in a training package with 1 or more other interventions? – specify package (s) | Implemented in all areas or selected areas - specify |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Home and Community(ORCs) | First level facility (BHUs) | Referral facility |  |  |
| Tetanus toxoid immunization |  |  |  |  |  | all |
| Birth and emergency planning |  |  |  |  |  | all |
| Detection and management of problems complicating pregnancy (e.g. hypertensive disorders, bleeding, malpresentations, multiple pregnancy, anaemia) |  |  |  |  |  | all |
| Detection and treatment of syphilis |  |  |  |  |  | all |
| Intermittent prophylactic treatment for malaria |  |  |  |  |  |  |
| Information and counseling on self-care, nutrition, safer sex, breastfeeding, family planning |  |  |  |  |  |  |
| Insecticide treated bed nets (LLIN) |  |  |  |  |  | In the malaria endemic and prone areas. |
| Prevention of mother to child transmission of HIV |  |  |  |  |  | all |
| Other: Iron folic acid, vitamin C and calcium supplementation to pregnant women |  |  |  |  |  | all |
| Other : (specify) _________ |  |  |  |  |  |  |
| Other: (specify) ________ |  |  |  |  |  |  |

WORKSHEET 3: Child health interventions and how they are delivered

BIRTH AND IMMEDIATE POST-NATAL PERIOD

| Interventions | Included in program? Tick if yes | Implemented at which levels? Tick levels |  |  | Implemented in a training package with 1 or more other interventions? – specify package (s) | Implemented in all areas or selected areas? - specify |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Home and Community | First level facility | Referral facility |  |  |
| Monitoring progress of labour, maternal and foetal well being with partograph |  |  |  |  |  |  |
| Active management of the third stage of labour |  |  |  |  |  |  |
| Social support (companion) during birth |  |  (at home) |  |  |  | all |
| Immediate newborn care (Resuscitation if required, Thermal care, Hygienic cord care, Early initiation of breastfeeding) |  |  |  |  |  |  |
| Emergency obstetric and neonatal care for complications |  |  |  |  |  |  |
| Antibiotics for preterm premature rupture of membranes |  |  |  |  |  |  |
| Antenatal corticosteroids for preterm labour |  |  |  |  |  |  |
| Prevention of mother to child transmission of HIV |  |  |  |  |  |  |
| Other : (specify) ________ |  |  |  |  |  |  |
| Other : (specify) _________ |  |  |  |  |  |  |
| Other : (specify) _________ |  |  |  |  |  |  |

WORKSHEET 3: Child health interventions and how they are delivered

NEWBORN PERIOD

| Interventions | Included in program? Tick if yes | Level at which intervention is delivered Tick levels |  |  | Implemented in a training package with 1 or more other interventions? – specify package (s) | Implemented in all areas or selected areas - specify |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Home and Community | First level facility | Referral facility |  |  |
| Exclusive breastfeeding |  |  |  |  |  |  |
| Thermal care |  |  |  |  |  | all |
| Hygienic cord care |  |  |  |  |  |  |
| Prompt care seeking for illness |  |  |  |  |  | all |
| Extra care of LBW infants |  |  |  |  |  |  |
| Management of newborn illness |  |  |  |  |  |  |
| Prevention of mother to child transmission of HIV |  |  |  |  |  |  |
| Other : (specify) _________ |  |  |  |  |  |  |
| Other : (specify) _________ |  |  |  |  |  |  |
| Other : (specify) _________ |  |  |  |  |  |  |

WORKSHEET 3: Child health interventions and how they are delivered

INFANTS AND CHILDREN

| Interventions | Included in program? Tick if yes | Level at which intervention is delivered Tick levels |  |  | Implemented in package with 1 or a training more other interventions? – specify package (s) | Implemented in all areas or selected areas - specify |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Home and Community | First level facility | Referral facility |  |  |
| Preventive interventions |  |  |  |  |  |  |
| Exclusive breastfeeding (<6 months) |  |  |  |  |  |  |
| Safe and appropriate complementary feeding with continued breastfeeding (at least up to 2 years) |  |  |  |  |  |  |
| Insecticide treated nets |  |  |  |  |  | Endemic areas |
| Immunization (BCG, Hepatitis B, DPT, OPV, Measles, Hib) |  |  |  |  |  |  |
| Vitamin A supplementation |  |  |  |  |  |  |
| Water, sanitation, hygiene |  |  |  |  |  |  |
| Birth spacing by > 24 months |  |  |  |  |  |  |
| Other : (specify) _________ |  |  |  |  |  |  |
| Other : (specify) _________ |  |  |  |  |  |  |
| Other : (specify) _________ |  |  |  |  |  |  |

WORKSHEET 3: Child health interventions and how they are delivered

INFANTS AND CHILDREN

| Interventions | Included in program? Tick if yes | Level at which intervention is delivered Tick levels |  |  | Implemented in a training package with 1 or more other interventions? – specify package (s) | Implemented in all areas or selected areas - specify |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Home and Community | First level facility | Referral facility |  |  |
| Treatment interventions |  |  |  |  |  |  |
| Oral rehydration therapy for diarrhea |  |  |  |  |  |  |
| Zinc for diarrhea |  | No stock |  |  |  |  |
| Antibiotics for dysentery |  |  |  |  |  |  |
| Antibiotics for pneumonia |  |  |  |  |  |  |
| Antimalarials |  |  |  |  |  |  |
| Management of severe malnutrition |  |  |  |  |  |  |
| Management of HIV-exposed/infected children |  |  |  |  |  |  |
| Other : (specify) _________ |  |  |  |  |  |  |
| Other : (specify) _________ |  |  |  |  |  |  |
| Other : (specify) _________ |  |  |  |  |  |  |

1.4.	Review Coverage indicators for child health

Review and discuss Worksheet 4: Coverage indicators for child health.  Each small group reviews a different level of the continuum of care (pregnancy, delivery and immediate post-delivery, neonatal period, infants and children 1-59 months).

For each measurement, ask the following questions:

- Are data available?

- Has the target been met? (if a target has previously been established)

- How has it changed over time?  Is it going up or going down?

- Does it differ between different regions or groups?

- Are there any problems with the validity or reliability of the data – are new or different methods needed?

Summarize your findings on Worksheet 4

Tick indicators with positive results

Trends are upwards

Targets have been met

Cross indicators with negative results

Trends are downwards or static

Targets have not been met

Significant differences exist between sub-groups

Shade indicators where data are needed

Describe how data will be collected in the future

Worksheet 4: Coverage indicators for child health

| Period | Intervention | Coverage measure | Baseline data (year and source) | Most recent data (year and source) | Target | Differences by region or group (highest/lowest) |
| --- | --- | --- | --- | --- | --- | --- |
| Pregnancy | Adequate antenatal care | Proportion of mothers who received at least 4 ANC visits | 70 % (AHB 2007) | 80% (KAP on MCH 2010) | 100% by 2015 | NA |
|  | Tetanus Toxoid to all pregnant women | Proportion of mothers who received TT2+ during pregnancy | 38.8% (2008 National EPI coverage survey) |  | >80% |  |
|  |  | Proportion of newborns protected at birth | 85.3% |  | >90% |  |
|  | Iron supplementation | Proportion of mothers/women who received iron during pregnancy | 80% as all ANC mothers receive |  | >90% |  |
|  | Malaria prevention | Proportion of pregnant women who slept under an ITN the previous night | NA |  | >95% in endemic areas |  |
|  | Voluntary counselling and testing for HIV and PMTCT | Proportion of HIV + mothers who received ART prophylaxis | NA |  | >95% |  |
| Labor and delivery | All deliveries by a skilled birth attendant | Proportion of deliveries by skilled birth attendants | 52% (AHB 2006) | 67% ( AHB 2010) | >85% |  |
|  |  | proportion of institutional births | 40% (AHB 2006) | 61% ( AHB 2010) | >80% |  |
|  | Identification and treatment of maternal emergencies such as eclampsia and obstructed labor | Proportion of rural pregnancies having a c-section | NA | NA | NA |  |
| Immediately after birth | Prevention of hypothermia | Proportion of babies who were dried, wrapped (and not bathed) immediately after birth | 40% (AHB 2006) proxy institutional delivery | 61% with proxy institutional delivery | 85% |  |

Worksheet 4: Coverage indicators for child health

| Period | Intervention | Coverage measure | Baseline data (year and source) | Most recent data (year and source) | Target | Differences by region or group (highest/lowest) |
| --- | --- | --- | --- | --- | --- | --- |
| Immediately after birth (continued) | Appropriate cord care and hygiene | Proportion of babies who had the cord cut with a clean instrument | 52% (AHB 2006) proxy skilled birth attendance | 67% (AHB 2010) proxy skilled birth attendance | 85% |  |
|  | Immediate initiation of breastfeeding | Proportion of mothers who initiated BF within 1 hour of birth | 81.5% (national nutrition, IYCF study 2008) |  | >85% |  |
|  |  | Proportion of babies who received a pre-lacteal feed | 10.7% (national nutrition, IYCF study 2008) |  | <5% |  |
| Postnatal/ neonatal period | Postnatal care visit | Proportion of mothers/newborns who had a care contact in the first 2 days after delivery | NA | NA | 80% |  |
|  | Exclusive breastfeeding | Proportion of mothers who did not give anything other than breastmilk in the first 3 days after birth | NA |  | 90% |  |
|  |  | Proportion of infants 0-28 days who are exclusively breastfed | 86% National Nutrition, IYCF study 2008 |  | 95% |  |
| Infants and children | Exclusive breastfeeding | Proportion of infants under 6 months exclusively BF | 10% National Nutrition, IYCF study 2008 |  | 35% | H=central region (14%) L= western region (8.2%) |
|  | Appropriate complimentary feeding | Proportion of infants 6-9 months who receive appropriate BF and comp feeding | 20.8% National Nutrition, IYCF study 2008 |  | 50% | NA |

Worksheet 4: Coverage indicators for child health

| Period | Intervention | Coverage measure | Baseline data (year and source) | Most recent data (year and source) | Target | Differences by region or group (highest/lowest) |
| --- | --- | --- | --- | --- | --- | --- |
| Infants and children (continued) | Micronutrient supplementation | Proportion of children who received a dose of vitamin A in the previous 6 m | 88% National Nutrition, IYCF study 2008 |  | 90% |  |
|  |  | Proportion of children living in HH that use iodised salt (15+ ppm) | 98.4% National Nutrition, IYCF study 2008 |  | Over 95% coverage |  |
|  | Immunizations against vaccine preventable diseases | Proportion of children 9-23 months of age vaccinated against measles before 12 m | 94.5% (2008) | 96% (2009 National EPI coverage survey) | Sustain >95% |  |
|  | Prevention of malaria | Proportion of children who slept under an ITN the previous night |  | NA |  |  |
|  | Antimalarial treatment for malaria | Proportion of children with fever who received appropriate antimalarials |  | NA |  |  |
|  | Care seeking for pneumonia | Proportion of children with suspected pneumonia taken to appropriate provider | NA | NA | 80% |  |
|  | Antibiotic treatment for suspected pneumonia | Proportion of children with suspected pneumonia who received appropriate antibiotics | NA | NA | 80% |  |
|  | Oral rehydration for diarrhea | Proportion of children with diarrhea who received ORT | NA | NA | 80% |  |
|  | Use of zinc for the treatment of diarrhea | Proportion of children with diarrhea who received ORT and a course of zinc | NA | NA | 80% |  |

Summary of Worksheet 4 – coverage  indicators

Coverage indicators - program is doing enough now

No. of household consuming iodized salt (+15ppm): 98.4%

Insecticide treated net in endemic areas: 100%

Immunization coverage: 98%

Vitamin A deficiency: 2.6% sub-clinical

Coverage indicators - program needs to do more

Exclusive breastfeeding for the first 6 months: 10%

Introduction of complementary food at 6-9 months: 20.8%

Access to safe drinking water:83%

ORT corner at the health facilities:31%

Access to excreta disposal: 91%

Step 3

How well are Activities Being Implemented?

Worksheet 5: Review how well the program implemented 	activities

1.5.	Review how well the program implemented activities

Review and discuss Worksheet 5: Review how well the program implemented activities.

Each small group completes one worksheet for a different level of the continuum of care (pregnancy, delivery and immediate postnatal period, newborn period, infants and children 1-59 months).  The review focuses on activities that have been planned or conducted since the last review.

For each activity area review:

Activity areas (left column):  Review the activity areas.  Decide whether or not activities have been implemented in this area.  Consider activities to deliver the key intervention packages.  Use workplans and administrative reports as well as field experience from all levels.  There is no need to write every activity planned or conducted into the table.  For each activity or group of activities, a decision needs to be made about the status of implementation (Task 2).  Make this decision as soon as the activities have been identified.

Status of implementation (second column): Based on program reports such as routine monitoring data, supervision reports, discussions with staff, or your own knowledge, describe whether activities have been implemented fully (eg. 10 completed out of 10 planned), partially (eg. 2 completed out of 5 planned), or not at all.

- Review output data to help with understanding how well implementation has been 	done (available data for each activity area has been summarized as supporting 	data).

- The status of implementation may be different between the national level, and sub-	national levels.  In addition, sub-national levels (regions or districts, for example) may 	also differ.  It is important to note these variations in this section.

Reasons for observed implementation performance (third column): List reasons that have contributed to the extent of implementation of the activity (fully, partly, not at all).  Program documents may state reasons, or you may have knowledge of some reasons.

Strengths and weaknesses of the program (fourth and fifth column):  Based on findings from the previous columns, discuss the main strengths and weaknesses for each activity area.

Worksheet 5:  Review how well the program implemented activities

__Pregnancy __Birth and Immediate Post-natal period__ Neonatal period __Infants and children 1-59 months

INTERVENTION PACKAGES BEING DELIVERED:______________________________________

| Activity area | Status of implementation (fully, partly or not at all) | Reasons for observed implementation Performance | Strengths | Weaknesses |
| --- | --- | --- | --- | --- |
| Policies, planning and management |  |  |  |  |
| Practice standards and guidelines updated and being used | IMNCI, growth monitoring, IYCF, PMTCT, VCT, FP, VHW manual, EPI manual, lactation manual, SAM manual | Standards revised and used by health workers | Strong political commitment. Uniform standards/guidelines. Committed health workers | Lack of expertise Shortage of human resources |
| Midwifery Standards, PPH Guideline | Old Midwifery Standard fully implemented, Revised Midwifery Standard and PPH guideline partly implemented | The Revised Midwifery Standard and PPH guideline partly implemented coz is recently revised and has some constraint in budget release | - Cover all the aspects of safe motherhood - Provided in all HFs - Updated as per the international standard | - Poor M&E - Assessment of impact not done |
| Newborn Standard | Fully implemented |  | Developed in 2006 and all BHU staffs and nurses were trained on the standard | Need to update Need to improve in terms of technical, and simplification and user-friendly |
| Essential drug list available | fully | EDL available and updated regularly | Std EDL in place | Interrupted drug supplies Dependent on other countries for supplies of drugs |
| Budgeted plans developed annually – at the national and district levels | fully | Annual work plan developed and implemented under specific budget | Work plan are developed on evidence based and in line with national goals Political commitment | Ad hoc activities crop up Lack of coordination between the programmes and districts at the time of planning |
| Planning done collaboratively with other divisions and with donors | fully | Annual work plan in place Plans reviewed regularly | Coordination within divisions under same department Support from the collaborating agencies | Poor inter-departmental coordination |
| Annual budget adequate to complete all activities in the last plan | partly | Unfunded activities are not being carried out | Strong support from government and partners | Implementation of district level activities are programme driven in terms of fund support Lack of resources Unfunded activities reflected in the AWP |

Supporting data:  policy and planning

| Indicator | Current status |
| --- | --- |
| Policies for exemption of pregnant women, newborns and children from health charges available and implemented | Y (free health service) |
| CRC reporting mechanism established and working | N |
| Costed national plan for ensuring universal access to newborn and child survival interventions available | Y |
| Mechanism for monitoring the International Code for Marketing of Breastmilk substitutes working | N |
| Laws and policies on vital registration adopted | N |
| National child health strategy endorsed and costed | N |
| % of districts implementing intervention package | 100% |
| % of proposed child health budget received on time in the previous year | Delay in receiving fund for the activities because of the financial procedures |

Worksheet 5:   Review how well the program implemented activities

__Pregnancy __Birth and Immediate Post-natal period__ Neonatal period __Infants and children 1-59 months

INTERVENTION PACKAGES BEING DELIVERED:______________________________________

| Activity area | Status of implementation (fully, partly or not at all) | Reasons for observed implementation Performance | Strengths | Weaknesses |
| --- | --- | --- | --- | --- |
| Human resources/training – in-service |  |  |  |  |
| Plan to ensure adequate staffing at each level | Partly | Lack of human resources Deployment problems | HRD master plan in place | Depend on other countries for specialized human resources Lack of effective deployment Inadequate capacity of training institute in the country |
| In-service training strategy available | Partly | HRD unable to initiate the process fully | In service training unit is being set up under HRD | Short term strategy most of the time Dependent on resources |
| In-service training conducted for health staff | Partly | Time and resource constraints | Training materials available Well trained facilitators | Release of staffs Poorly coordinated in- service training amongst the programmes |
| In-service facilitators trained | fully | Identified and trained facilitators | Good commitment to train | Release of facilitators Time and resources constraints |
| Follow-up after in-service training conducted | Partly | Time and resources constraints | Proposed (recommended by the annual health conference 2008) | Lack of follow up plan and resources |
| Quality of in-service training – are: types of staff trained, materials used, time allocated, amount of clinical practice adequate? | Partly | Lack of cases for clinical practice | Need based trainings conducted Standard training tools used | Lack of cases for clinical practice No training quality assessment done Quality compromised during cascade trainings |

Worksheet 5:  Review how well the program implemented activities

__Pregnancy __Birth and Immediate Post-natal period__ Neonatal period __Infants and children 1-59 months

INTERVENTION PACKAGES BEING DELIVERED:______________________________________

| Activity area | Status of implementation (fully, partly or not at all) | Reasons for observed implementation Performance | Strengths | Weaknesses |
| --- | --- | --- | --- | --- |
| Human resources/training – pre-service |  |  |  |  |
| Pre-service training strategy available | Not at all |  | Lecturers and structured curriculum in place | Current orientation program does not cover all program aspects |
| Pre-service training incorporated into curriculae of medical and other schools | fully | Structured curriculum in place | Incorporating revised manual in curricula Revision of curriculum as per need and regularly |  |
| Pre-service trainers trained | fully | Lecturers are fully trained | Qualified lecturer | Lack of adequate number of lecturers at the institute |
| Quality of pre-service training – materials used (including textbooks), time allocated amount of clinical practice adequate? | partly | Resource constraints | Although limited cases for practical sessions, equal opportunity for the trainees are allocated | Not enough text books for teaching Inadequate time allocation for the clinical sessions |

Supporting data:  human resources/ training

| Indicator | Baseline data (year and source) | Most recent data (year and source) | Target | Differences by region or group (highest/lowest) |
| --- | --- | --- | --- | --- |
| % of health staff who have received training in intervention package = |  |  |  |  |
| IMNCI | 70% (2010) |  | 98% |  |
| EPI | 95% |  | 95% |  |
| Lactation management | 80% (2007) |  | 100% |  |
| IYCF | <10% (2010) |  | >80% |  |
| SAM (all district hospitals) | 20% (2003) | 35%(2010) | >80% |  |
| RH (midwifery and newborn care) |  |  |  |  |
| % of planned trainings completed in the previous year = | 14/15 activities completed |  |  |  |
| % of health facilities with at least 60% of health workers caring for children, newborns or pregnant women trained in training package = | NA |  |  |  |
| % of all trained staff who receive follow-up visit within 3 months of training = | NA |  |  |  |
| % of medical/nursing/midwifery training schools that have incorporated focus intervention or package = | 100% |  | 100% |  |
| % of mothers who receive ANC/PNC from a skilled provider = | 70% (AHB 2007) | 80% ( KAP _MCH, 2010) | 100% |  |

Worksheet 5:  Review how well the program implemented activities

__Pregnancy __Birth and Immediate Post-natal period__ Neonatal period __Infants and children 1-59 months

INTERVENTION PACKAGES BEING DELIVERED:______________________________________

| Activity area | Status of implementation (fully, partly or not at all) | Reasons for observed implementation performance | Strengths | Weaknesses |
| --- | --- | --- | --- | --- |
| Health communication/IEC |  |  |  |  |
| Child health communication strategy or plan available | partly | EPI communication strategy is available but may not cover all aspects of child health | Conducted KAP survey on MCH and Communication strategy on MCH is under process | No actual communication strategy or plan available |
| Focus on reaching hard to reach populations | Partly | Geographical terrain Nomadic Unreached urban population | Policy and strategies in place | Rough terrain and dispersed population Socio cultural beliefs Lack of awareness among the population |
| Communication activities conducted: mass media, printed materials, training for local groups/volunteers in inter-personal communication; training for health workers | Fully | Integrated in various program | High coverage to media Communication modules and materials are available in the health facilities | No regular update of the information and messages (need based) Poor M&E/review High cost of media usage Health workers are not train on IPC |
| Messages and materials developed and distributed | Fully | Need based materials developed | Available | Lack of impact study |
| Quality: key child health messages used; messages and materials pre-tested and adapted for local context | Fully | Need based materials developed and distributed | Available | Lack of impact study |

Worksheet 5:  Review how well the program implemented activities

__Pregnancy __Birth and Immediate Post-natal period__ Neonatal period __Infants and children 1-59 months

| Activity area | Status of implementation (fully, partly or not at all) | Reasons for observed implementation performance | Strengths | Weaknesses |
| --- | --- | --- | --- | --- |
| Development of community supports |  |  |  |  |
| Implementation plan for community-level activities available | Fully | Structured plan for the community activities | Annual plan for the community activities available Good coverage | Time constraint (too many activities at a time) Inadequate human resources |
| Community health workers trained and available | Fully | well trained BHU staffs | Well structured curriculum in place for the BHU staff training (RIHS) | Inadequate clinical practices |
| Volunteers (VHWs) trained and available | Fully | Need based | Community participation Low cost | Dropout rate Responsibility and accountability is low Low education level |
| Quality: developed collaboratively; use local staff and volunteers; supervision or oversight plan Included | Partly | Yearly plan for the community health workers (VHW) | Focus on primary health care | Purely a voluntary services Responsibility and accountability is low Low education level |

Supporting data:  health communication/ community

| Indicator | Baseline data (year and source) | Most recent data (year and source) | Target | Differences by region or group (highest/lowest) |
| --- | --- | --- | --- | --- |
| % of mothers receiving at least one mass media communication activity (radio, TV, groups etc) which includes the key interventions in the he last 3 months = | NA | 54% radio (KAP survey 2010) | 80% |  |
| % of caregivers who know 2 danger signs for seeking care during pregnancy/for their sick child = | NA | 28.1% (KAP survey 2010) | 70% |  |
| % of trained VHWs for promoting key family and community practices = | NA | 30% | 100% |  |
| % of caretakers of children 0-59 months who received a home visit and counseling from BHU health provider in the previous 3 months = | NA |  | 80% |  |

Worksheet 5:  Review how well the program implemented activities

__Pregnancy __Birth and Immediate Post-natal period__ Neonatal period __Infants and children 1-59 months

| Activity area | Status of implementation (fully, partly or not at all) | Reasons for observed implementation performance | Strengths | Weaknesses |
| --- | --- | --- | --- | --- |
| Strengthening health systems |  |  |  |  |
| Quality of case-management | fully | Trained health staffs on the case management | In service training packages in place Annual work plan for training | Human resource constraints Not all staffs get timely in service training In appropriate work distribution |
| Services available | fully | Well established health facilities | At least one health staff in every health facilities | Human resource constraints Not all staffs get timely in service training In appropriate work distribution Communication/transport constraint |
| Essential drugs and equipment available at first and referral levels | fully | DVED is solely responsible for procurement and supplies of drugs and equipment | List of EDL is in place Maintaining 95% of drug supply is mandatory Central distribution in place | Supplies not regular |
| Routine supervision conducted using checklists, and observation of practice | partly | Check list not yet endorsed |  | Time and resource constraints |
| Systems for timely referral of sick newborns and children in place | fully | Well established referral system in place Health workers trained Ambulance facilities available Hotline services available | Well established referral system in place | Travel distance Difficult terrain Cultural and traditional beliefs Running cost for ambulance |

Supporting data:  systems

| Indicator | Baseline data (year and source) | Most recent data (year and source) | Target | Differences by region or group (highest/lowest) |
| --- | --- | --- | --- | --- |
| Quality of case-management |  |  |  |  |
| % of children who received integrated assessment (10 assessment tasks) - IMNCI | NA | initiated |  |  |
| % of children attending facilities who need an antibiotic and/or an antimalarial who are prescribed the medicine correctly - IMNCI | NA | initiated |  |  |
| Data on quality of antenatal care, delivery or newborn care | NA | NA |  |  |
| Services available |  |  |  |  |
| % of hospitals providing comprehensive emergency obstetric and newborn care (24 hours/day, 7 days/week) = | 4/29*100=14% (2000,RH) | 7/30*100=23% (2009, RH) | 50% by 2013 |  |
| % of hospitals or maternity facilities accredited as baby-friendly in the previous 2 years = | NA | Revitalization on process | 10 |  |
| % of facilities with immunization services available = | 100% | 100% | 100% |  |
| % of facilities providing ANC, delivery, PNC, IMNCI services = | NA | 100% | 100% |  |
| % of mothers receiving +4 ANC/ PNC from a skilled provider | NA | 44% ( ANC) NA (PNC) | 80% 80% |  |
| Essential drugs, equipment and supplies |  |  |  |  |
| % of health facilities with all essential medicines for managing common newborn and childhood illnesses | NA | 100% in all the health facilities except some services | 100% |  |
| % of health facilities with all essential medicines for managing obstetric emergencies | NA | 100% | 100% |  |
| % of health facilities with all equipment and supplies for vaccination | NA | 100% | 100% |  |
| % of facilities with basic equipment and supplies for managing sick newborns and children | NA | 100% in all hospitals and BHU-1 | 100% |  |
| % of facilities that manage severely ill children with oxygen/delivery systems available in the pediatric ward | NA | 100% | 100% |  |
| Supervision and referral |  |  |  |  |
| % of health facilities receiving at least one supervisory visit with observation of case-management in the previous 6 months | NA | NA | Once in 6 months |  |

Worksheet 5:  Review how well the program implemented activities

__Pregnancy __Birth and Immediate Post-natal period__ Neonatal period __Infants and children 1-59 months

| Activity area | Status of implementation (fully, partly or not at all) | Reasons for observed implementation performance | Strengths | Weaknesses |
| --- | --- | --- | --- | --- |
| Monitoring and evaluation |  |  |  |  |
| Plan for routine monitoring and periodic evaluation of the child health program included in strategic plan and work plans | partly | For IMNCI follow up supervision once in 6 months | Supervisors are trained on IMNCI | Comprehensive M&E plan not in place Not all relevant health workers are trained |
| Standard international indicators used | Fully | Uniform standards | Uniform standards | International standards might not be used to country context |
| Short and long term targets set | partly | No baseline data |  | Lack of specific strategy and programs |
| Population- and health facility-based data available for monitoring and evaluation | fully | Morbidity and activity reporting from the districts in place Annual household survey report | HMIS data collection system is in place Recording and reporting on regular basis HMIS soft ware in place and trained in recoding and reporting | Reports not uniform across health facilities (cumulative Vs new cases) Need to update HMIS manual Some indicators are not available (PNC/breastfeeding) Not reliable data from Annual household survey (AHS) Major cities not included in the AHS |
| Monitoring data used for routine planning by all levels | Partly | Data collected are not analyzed systematically | Annual household survey Routine morbidity and activity reporting | Weak culture of information usage |
| Vital registration systems working | Not working at all | No policies and laws on vital registration |  |  |

Supporting data:  monitoring and evaluation

| Indicator | Baseline data (year and source) | Most recent data (year and source) | Target | Differences by region or group (highest/lowest) |
| --- | --- | --- | --- | --- |
| % of births registered at birth = | NA |  |  |  |
| % of child deaths registered = | NA |  |  |  |
| % of routine reports from districts received on time | 88% (2009) | 85% (2 qtr of 2010) | 100% |  |

Step 4

Identify the main problems the program has faced

1.5.	Identify the main problems

Each small group completes one Worksheet 6 – identify the main problems for a different level of the continuum of care (pregnancy, delivery and immediate postnatal period, newborn period, infants and children 1-59 months).

For each activity area review and summarize the weaknesses identified on Worksheet 5.

Summarize these as the most important problems – no more than 3 or 4 in each main activity area.  These problems will be presented and discussed in the large group.

A final list of the most important problems for each activity area will be developed in the large group – problems that are common will be grouped together.

Worksheet 6:  Identify the main problems

__Pregnancy __Birth and Immediate Post-natal period__ Neonatal period __Infants and children 1-59 months

Interventions where more action is needed (from coverage data):_________________________________

Intervention packages used to deliver the interventions: ____________________________________

| Activity Area | Problems |
| --- | --- |
| Policy, planning and management | Lack of knowledge and skills in the program planning and management Unfunded activities reflected in the AWP/ Ad hoc activities No mandatory vital registration Inadequate/quality of data on ANC/PNC/neonatal deaths/immunization coverage |
| Human resources and training | Dependence on other countries for most HR development and resources No long term in-service training plan/ strategy Release of field staff and facilitators for in-service trainings Deployment of skilled human resources Lack of patients for clinical practices during in service training PRE-SERVICE Inadequate number of clinical supervisors Inadequate resource materials Inadequate time for Practicum |
| Communication | No communication strategy and action plan for child health (Regular update of information and messages not carried out; nutrition, VPDP, RH, IMNCI) Socio-cultural beliefs Quality of IEC provided in the MCH |

WORKSHEET 6: Identify the main problems (continued)

| Activity Area | Problems |
| --- | --- |
| Development of community supports | Inadequate human resource Competing activities from different programmes Low responsibility and accountability of village health workers (VHWs) due to their voluntary nature Educational level of VHWs |
| Strengthening health systems | Inadequate human resource Inadequate coverage of in-service training for all health workers Unequal work distribution Interrupted supply of medicines Difficult terrain/logistics for timely referral Quality of services provided in the MCH |
| Monitoring and evaluation | No follow up after in service trainings Lack of regular monitoring and supervision No M & E system in place Lack of M & E skills |

Step 5

Develop solutions and recommendations

1.5.	Develop Solutions and recommendations

Worksheet 7 – develop solutions and recommendations is completed for the final list of problems identified after Step 4.

For each activity area possible causes, and solutions to problems will be discussed.  Recommendations for what the program can do in the next workplan are developed.

Solutions should:

- Address causes of problems

- Be feasible with available human, material and financial resources

- Build on existing program activities when possible

Recommendations should:

- Be as specific as possible

- Focus on concrete actions

Worksheet 7: Develop solutions and recommendations

Activity area:  Policy, planning and management

| Problem | Cause | Solution |
| --- | --- | --- |
| Lack of knowledge and skills in the program planning and management | No system of mandatory training for program officers on program planning and management | All program officers/DHOs to be mandatorily trained on program planning and management |
| Unfunded activities reflected in the AWP/ Ad hoc activities | Emergencies/outbreaks | Minimized unfunded activities |
| No proper data on births and deaths | No adequate mechanism for vital registration Data on neonatal deaths at home were difficult to collect due to lack mandatory registration Cultural beliefs leading to non disclosure of neonatal deaths | Develop a mechanism for vital registration Support implementation of the updated mechanism of vital registration |
| Inadequate/quality of data on ANC/PNC/neonatal deaths/immunization coverage | PNC was not adequately addressed | At least one home visits by the health workers within 72hrs for home deliveries and within one week for institutional deliveries |
| Recommendations: - To form Child Health Advisory Committee(CHAC) at the MoH to guide and provide technical assistance to all child health related programs - All existing program officers including DHOs to be mandatorily trained on program planning and management - To reduce the neonatal and maternal mortality postnatal home visit should be made mandatory - PNC guidelines and home visit check list to be developed for BHU health workers - In collaboration with MoHCA and NCWC, develop a mechanism for vital registration - Support implementation of the updated mechanism of vital registration through training, supervision, monitoring and evaluation - Early childhood care and development (ECCD) is an important component of IMNCI and has it be incorporated in the IMNCI module. - To complete the linkage between the BHUs and hospitals on IMNCI referral the WHO module on hospital based IMNCI should be adopted and the capacity of health workers should be built - The child health program (RH, Nutrition, EPI, IMNCI, ARI/CDD) review should be conducted twice in five year plan |  |  |

Activity area:  Human resources/training

| Problem | Cause | Solution |
| --- | --- | --- |
| Dependence on other countries for most HR development and resources | No national capacity for degree courses | Hospital attachments to enhancing skills Establishment of specific training centre |
| In service training planned on annual basis only | No long term in-service training plan/ strategy | Five year training plans for each program |
| Release of field staff and facilitators for in-service trainings | Too many trainings and less staffs | Coordinate all trainings through HRD |
| In appropriate deployment of skilled human resources | Poor HR management and lack of coordination | Deployment as per the facility needs in coordination with relevant stakeholders |
| Inadequate hands on training | Lack of patients for clinical practices during in service training | Identify hospitals with enough case loads for training purpose |
| PRE-SERVICE |  |  |
| Quality of services provided by the health workers | Inadequate number of clinical supervisors Inadequate resource materials Inadequate time for clinical practice | Increase the number of clinical supervisors Procure adequate teaching materials Explore more health facilities for clinical practice: e.g lungtenphu hospital |
| Recommendations: - Identify health facilities for in/pre service practical attachment - Conduct assessment of the quality of services provided by the health workers - HRD to improve the coordination of in service trainings - HRD to deploy health workers based on their skills - One month pre-service orientation program for all new health workers on program aspects (RIHS, medical officers and other graduates) |  |  |

Activity area:  Communication/IEC

| Problem | Cause | Solution |
| --- | --- | --- |
| Poor ANC +4 visits (44%) Poor PNC coverage. Exclusive breastfeeding (10%) Early introduction of complementary feeding. | Inadequate/Poor Quality of IEC provided in the MCH clinics. No communication strategy and action plan for child health (Regular update of information and messages not carried out; nutrition, VPDP, RH, IMNCI) Socio-cultural beliefs | Develop a concrete communication strategy and action plan for child health. |
| Recommendations: - Form a working group to develop a communication strategy and action plan for child health. - Ensure budget for communication action plan. - Promotion of maternal nutrition program to reduce low birth weight |  |  |

Activity area:  Development of community supports

| Problem | Cause | Solution |
| --- | --- | --- |
| Insufficient utilization of community support. | Competing activities from different programmes Educational level of VHWs | Draw ToR for VHWs Prioritize activities for VHWs. Strengthen monitoring and supervision. |
| High dropout rate of VHWs | Lack of motivation. Lack of incentives. | Explore incentives for VHWs Develop other forms of motivation. |
| Recommendations: - Review effectiveness of the VHW program - Health workers should carry out supportive supervision of the VHWs - Sustain the incentives that are currently in place and find other forms of motivation/incentives - Sustain annual regular training for VHWs - Organize meeting with the best two VHWs from each Dzongkhags once in two years - Development and implementation of community health package |  |  |

Activity area:  Strengthening Health Systems

| Problem | Cause | Solution |
| --- | --- | --- |
| Inadequate human resource at the BHU level | Irrational deployment of health workers. Female HA’s not willing to go to remote BHUs Spouse working in other sectors. | HR/Dzongkhags to deploy staff based on work load. |
| Inadequate coverage of in-service training for certain categories of health workers | Improper training plan. Only one time training is conducted for a particular activity | Proper training plan to cover all the health workers. |
| Shortage of some essential drugs | Interrupted supply of medicines | DVED to follow up with emergency procurement. |
| Recommendations: - Reinforce the existing RCSC rule of rural placement by HR/Dzongkhags - Conduct audit of under five deaths to find causes of child deaths and identify area to focus |  |  |

Activity area:  Monitoring and evaluation

| Problem | Cause | Solution |
| --- | --- | --- |
| No follow up after in service trainings | No follow up plan in place for most training programs. | Institute a follow up plan after every training. |
| Lack of regular monitoring and supervision | Lack of M & E skills Lack of easy to use uniform for monitoring of child health interventions No M & E system in place | Develop skills of the supervisors through training. Conduct M&E as per MoH’s mandate. Introduce simple visualized monitoring forms |
| Recommendations: - To implement continuum of care monitoring at BHU and district level\ - Institute a follow up plan after every training. - ToT and cascade training including monitoring and after-training supervision to be budgeted together. - Conduct impact assessment on the trainings/interventions. |  |  |

SOWC 2010

SOWC  2008 and 2009

Socio-economic and demographic indicators 2005, National Statistics Bureau, August 2008

Nutrition Survey, 2008

ibid

Socio-economic and demographic indicators, National Statistics Bureau, Aug 2008

Nutrition Survey, MoH, 2008

ibid

Report from Celebration 30 years of PHC Alma Ata Declaration, Thimphu, 2008

SOWC 2009

Child Health Epidemiology Review Group (CHERG), Nov 2006

Nutrition Survey Report, 2008

ibid

BLSS report 2007

EPI Survey Report, 2008

ibid

KAP MCH Survey Report,2010

ibid

Nutrition Survey Report, 2008